## User Story
# | Epic | User Story | Component | Priority order | Owner | Status
1 | Test image segmentation library | Create an Android app that accesses live video from camera | Android App |  |  | Complete
2 | Test image segmentation library | Identify the Deep lab library that provides good image segmentation output for human objects | Python library |  |  | Complete
3 | Test image segmentation library | Develop Python code to process an image, extract the human foreground from the image and display with a virtual background | Python library |  |  | Complete
4 | Test image segmentation library | Optimize virtual background and image segmentation logic | Python library |  | Shobhit, Shaashwat | Complete
5 | Test image segmentation library | Implement image segmentation logic in the Android application | Android App, Python library |  |  | Complete
6 | Test image segmentation library | Display the output (human foreground with virtual background) in the Mobile app | Android App |  |  | Complete
7 | Test image segmentation library | Upgrade Android SDK to use latest camera features | Android App |  | Alankrit | Complete
8 | Video calling App | Integrate phone contacts and display contacts list in UI | Android App
9 | Video calling App | Build framework to sign in and sign out of the app | Android App
10 | Video calling App | Implement video calling framework (e.g. WebRTC, Agora.io) for the Android app | Android App |  |  | Complete
11 | Video calling App | Add option to select contact and initiate video call | Android App |  |  | Complete
12 | Video calling App | Develop UI panels to show caller and receiver video | Android App |  |  | Complete
13 | Video Call Merge | Develop Python function to obtain caller's image, receiver's image and virtual background as inputs and produce a merged image (foregrounds from the two images on the virtual background) | Python library |  | Shobhit, Shaashwat | Complete
14 | Video Call Merge | Develop the merge feature in Native Android (Java) | Android App |  | Shobhit, Shaashwat | In progress | Focus for week of 5/1
15 | Video Call Merge | Capture image frame from caller's and receiver's video stream | Android App |  | Alankrit | In progress | Focus for week of 5/1
16 | Video Call Merge | Add feature in Android app that initiates image merge by clicking the merge button to transform the two panel screen into one panel screen | Android App |  | Alankrit | In progress
17 | Video Call Merge | Call the merge function in Java and provide the caller's image, receiver's image and a default virtual background as inputs and display the output from the function in the app's UI panel | Android App, Python library |  | Shobhit, Shaashwat | In progress | Focus for week of 5/1
18 | Video Call Merge | Optimize the video and resize the video | Python library |  | Shobhit, Shaashwat | In progress | Focus for week of 5/4
19 | Capture image & video | Provide option to capture image during a video call and save to photo library | Android App |  | Alankrit
20 | Capture image & video | Provide option to capture video during a video call and save to video library | Android App |  | Alankrit
21 | Integration with Social media | Provide option to integrate with Facebook and post photos and videos on Facebook | Android App |  | Alankrit
22 | Merge in Live background | Enhance the merge function to use the caller's live background and merge the receiver's foreground (human object) to the merged video | Python library |  | Shobhit, Shaashwat |  | Focus for week of 5/1

## Additional user stories
Scale image to bring in similar size
Light tone adjustment
Ability to make video call between 2 individuals (in Android)
Implement virtual background for real time video
Custom backgrounds ​
Merge Video/ Image​
Import Contacts to the App from phonebook​
Invite new users to the App​
Video call with 2 users​
Gallery of all selfies taken using the app (also stored in photos)​
Identify primary human objects from the foreground
Android compatibility​
Chat / instant message​
Chat history search​
Live backgrounds (caller / receiver)​
Record merged video​
Video call with up to N users​
Camera Filters (Color, black and white, studio mode, portrait mode, Night mode, … )​
In the merged video, zoom in/ zoom out one of the foregrounds (person)​
In the merged video, move one of the foregrounds (person) relative to the other other foreground (person)​
Record video